## Sheet1
Topic | Priority | Mynd Status | Schedule Walk through | Current Status | Remarks
MIS Dashboard for Corporate | VERY HIGH | Done | 1st April | Walkthrough done yesterday | Observations shared in attached mail – need to deploy 100% with accurate data validation by today
MIS Dashboard - Transaction data export facility | VERY HIGH | New Requirement
Remaining reports | VERY HIGH | Change in requirement |  | Night driving, Vehicle and driver details report need extra fields | Extra fields have been shared in attached sheet and these fields to be added
Vehicle inspection + Overspeeding + Continuous driving report | VERY HIGH | New Requirement |  | Vehicle inspection + Overspeeding + Continuous driving report | To be discussed with Amit and Jayram in loop
SRN Workflow steps removal | VERY HIGH | New Requirement |  | Under discussion | To be discussed with Amit and Jayram in loop
MO Additional changes | VERY HIGH | New Requirement
UAT Remaining points - Auto trip planning | HIGH | WIP | 3rd April | WIP | Mynds team to confirm deployment and schedule walkthrough
3D Simulation | HIGH | Done | 1st / 2nd April | WIP | Mynds team to confirm deployment and schedule walkthrough
Push Notification on mobile application | HIGH | Done | 1st / 2nd April | WIP | Mynds team to confirm deployment and schedule walkthrough
Rating Engine | LOW | WIP | 3rd April | WIP | Mynds team to confirm deployment and schedule walkthrough