## Sheet2
SN | Particulars | SPOC | Remarks
0 | Mail helpdesk to be set - Details to be shared for Setup | All
A. | Vendor Onboarding Module
| Clarify and update Email contents for Vendor Onboarding | Mynd
| Clarify and update Email contents for Vendor Training Manual | Mynd
| Reconsider from AP Validation and treasry team will go to Vendor Payment Team instead of Vendor | Mynd
| New pdf file only with Terms and Conditions to be genetrated and attached in Vendor Registartion confirmation mail | Mynd
| Final review and Go Ahead on Vendor Onboarding Module | Paytm
| Validation of Masters | All
| Go Live preparation | Mynd
B. | Budget to PO
| Budget to PO UAT obsevation finalisation | Paytm
| Budget to PO Mail template updation | Mynd
| Company wise series for PR, PES and PO -final decision | Paytm | Mr Udit to internally disucss and confirm on process for PO /PR document series updation from SAP
| PO Modification - Impact on Integration | Paytm
| Integration files updation | Mynd
| Integration files testing | All
| Training to Arpit on Integartion file handling during testing | Mynd
| Integration exception handling Approach - Action plan | SAP Team
| PO T&C from Paytm Legal | Paytm
C. | Invoice to Payment
| Invoice to Payment UAT Observation finalisation | Paytm
| Invoice to Payment Mail conents | Paytm
| Integration files testing - Invoice Lifecycle | Paytm
| Integration files testing - GRN | All
| Integration files testing - Payment | All
| Integration files testing - Invoice Lifecycle - Invoice attachment | All, SAP